## Sheet1
Task No. | Task | Start Date | Planned Completion Date | Duration (days)
1 | Project Proposal Presentation | 2020-09-02 | 2020-09-09 | 8
2 | Brainstorm gameplay mechanics | 2020-09-09 | 2020-09-21 | 13
3 | Create Unreal project | 2020-09-21 | 2020-09-21 | 1
4 | Complete Unreal tutorial | 2020-09-21 | 2020-09-28 | 8
5 | Figure out camera placement | 2020-09-21 | 2020-09-28 | 8
6 | Write Project Requirements Doc | 2020-09-23 | 2020-09-30 | 8
7 | Make Preliminary Schedule | 2020-09-23 | 2020-09-30 | 8
8 | Generate hex board / hex tiles placement | 2020-09-28 | 2020-10-06 | 9
9 | Castle, outposts, and roads placement | 2020-10-06 | 2020-10-20 | 15
10 | Test multiplayer config | 2020-10-13 | 2020-10-20 | 8
11 | Add resource generation | 2020-10-16 | 2020-10-27 | 12
12 | Add zombie horde logic | 2020-10-27 | 2020-11-10 | 15
13 | Add different victory paths | 2020-11-03 | 2020-11-13 | 11
14 | Add military encounter mini-game | 2020-11-14 | 2020-11-24 | 11
15 | Gather test players | 2020-11-17 | 2020-11-24 | 8
16 | Collect feedback from test players | 2020-11-24 | 2020-12-01 | 8
17 | Refine gameplay mechanics | 2020-11-30 | 2020-12-11 | 12
Formulas:
Duration (days) = DATEDIF([Start Date], [Planned Completion Date],"d") + 1